## Sprint 1 Backlog
Story #	Sprint Backlog Item	Task #	Volunteer	Task Details	Initial Effort Estimate (hrs)	New Estimates of Effort remaining at end of					Status
				Day1	Day2	Day3	Day4	Day5	Day6
US001	As a…. / I want to ….. / So that I can ….As a…. / I want to ….. / So that I can ….	Task 1	Ram	Write a program for displaying the home page	5	4	4	0				Closed
		Task 2	Satish	Design the UI for the Home page	4	3	3	1				In Progress
		Task 3	Vidya	Design and create the DB fields	5	3	4	2				In Progress
		Task 4	Priya	Write test conditions to test the home page	3	3	3	3				Open
		Task 5	Ram	----	2	2	2	2				Open
		…	…	----	--
		Task n	…	Execute the tests	--
US002	As a…. / I want to ….. / So that I can ….As a…. / I want to ….. / So that I can ….	Task 1	Lakshmi	----	6	6	6	6				Open
		Task 2	Priti	----	5	5	4	0				Closed
		Task 3	Ninad	----	5	3	2	2				In Progress
		Task 4	John	----	4	2	0	0				Closed
		…	…	----	--
		Task n	…	----	--
…..					--
US009					--
				Total	300	260	220	160

## Sprint 1 Burndown Chart
				Sprint Timeline / Remaining Effort (hrs)

Day0	Day1	Day2	Day3	Day4	Day5	Day6
300	260	220	160	90	65	0

300	250	200	150	100	50	0